## Tasks
Outline Level | Name | Duration | Resource Names | Predecessors | Materials
1 | B-M
2 | Beam assembly
3 | Cross-beam axes | 28800 | Mechanic |  | PART-0001, PART-0002
3 | Services | 14400 | Mechanic |  | PART-0003
3 | Electro-spindle installation | 14400 | Mechanic | Cross-beam axes, Services | PART-0004
2 | Base frame
3 | Base slides | 21600 | Mechanic |  | PART-0005
3 | Vises | 14400 | Mechanic | Base slides | PART-0006, PART-0007
3 | Hydraulic unit | 10800 | Mechanic | Vises | PART-0008
2 | Commissioning
3 | Electrical hook-up | 28800 | Electrician | Electro-spindle installation, Hydraulic unit | PART-0009
3 | Testing | 21600 | Tester | Electrical hook-up
3 | Painting | 14400 | Painter | Testing | PART-0010